## Sprint Overview
WORK ORDER MODULE - 5 DAY SPRINT
Sprint Duration: | April 27 - May 1, 2026 (5 Days)
Team: | Backend Dev 1, Backend Dev 2, Frontend Dev
Sprint Objective:
Deliver MVP Work Order Module with core functionality:
✓ Email-based work order creation with AI extraction
✓ Basic approval workflow
✓ Work order listing and details view
✓ Status tracking and updates
✓ Basic CMMS integration (mock)
DAILY MILESTONES |  |  |  | RISK MITIGATION
Day | Date | Milestone | Deliverables | Risk: AI integration complexity
Day 1 | Mon Apr 27 | Foundation Setup | Database schema, API skeleton, Email parsing POC | Mitigation: Use simple prompt, mock if needed
Day 2 | Tue Apr 28 | Core Backend Complete | Work order CRUD, Email processor, AI extraction working
Day 3 | Wed Apr 29 | Frontend MVP | List/detail views, Create form, API integration | Risk: CMMS integration delays
Day 4 | Thu Apr 30 | Integration & Polish | Approval workflow, Status updates, Bug fixes | Mitigation: Mock interface, stub responses
Day 5 | Fri May 1 | Testing & Demo | End-to-end testing, Demo preparation, Documentation
Risk: Scope creep
SUCCESS CRITERIA |  |  |  | Mitigation: MVP only, defer Step 3-15 to Phase 2
☑ User can send email to create work order
☑ AI extracts asset, location, issue from email
☑ Work order appears in list with status
☑ User can view work order details
☑ Approval workflow functional
☑ Status can be updated
☑ Demo-ready by Friday EOD

## Backend Dev 1
BACKEND DEVELOPER 1 - TASK LIST
Focus: Database, API Core, Email Processing
ID | Day | Task | Description | Effort (hrs) | Dependencies | Status | Claude Code Prompt | Priority | Notes
BE1-01 | Day 1 | Database Schema | Create work_orders table with all required fields | 2 | None | Not Started | Create PostgreSQL schema for work_orders table with fields: work_order_id, source, asset, location, issue_description, priority, status, created_at, etc. | Critical | Use provided schema
BE1-02 | Day 1 | API Project Setup | Initialize FastAPI project, folder structure, dependencies | 1 | None | Not Started | Set up FastAPI project with folder structure: /api, /models, /services, /db. Include requirements.txt with fastapi, uvicorn, sqlalchemy, anthropic | Critical
BE1-03 | Day 1 | Database Models | Create SQLAlchemy models for work_orders | 1.5 | BE1-01 | Not Started | Create SQLAlchemy ORM models for WorkOrder with all fields matching schema | Critical
BE1-04 | Day 1 | Email Parser POC | Build email parsing function with sample data | 2 | None | Not Started | Create email parser that extracts subject, body, from, and stores in dict. Test with sample email | High | Mock Outlook integration
BE1-05 | Day 1 | Basic CRUD Endpoints | GET, POST work orders endpoints | 2 | BE1-03 | Not Started | Create FastAPI endpoints: POST /work-orders, GET /work-orders, GET /work-orders/{id} | Critical
BE1-06 | Day 2 | AI Extraction Service | Claude API integration for email extraction | 3 | BE1-04 | Not Started | Create service class that calls Claude API to extract asset, location, issue from email text. Return structured JSON | Critical | Use simple prompt
BE1-07 | Day 2 | Email Work Order Flow | Complete email → work order creation | 2 | BE1-06 | Not Started | Integrate email parser + AI extraction + work order creation into single flow | Critical
BE1-08 | Day 2 | Status Update Endpoint | PATCH /work-orders/{id}/status | 1 | BE1-05 | Not Started | Create endpoint to update work order status with validation | High
BE1-09 | Day 2 | Search & Filter | Add query params to list endpoint | 2 | BE1-05 | Not Started | Add filters to GET /work-orders: status, priority, asset, date range | Medium
BE1-10 | Day 3 | Approval Endpoint | POST /work-orders/{id}/approve | 2 | BE1-05 | Not Started | Create approval endpoint that changes status and records approver | High
BE1-11 | Day 3 | Mock CMMS Integration | Stub CMMS send function | 1.5 | BE1-05 | Not Started | Create mock CMMS service that logs work order and returns success | Medium | Can be stubbed
BE1-12 | Day 3 | Validation Layer | Add input validation and error handling | 2 | BE1-05 | Not Started | Add Pydantic models for request validation and proper error responses | High
BE1-13 | Day 4 | Error Handling | Comprehensive error handling across all endpoints | 2 | BE1-12 | Not Started | Add try-catch blocks, proper HTTP status codes, error messages | High
BE1-14 | Day 4 | API Documentation | Auto-generate OpenAPI docs | 1 | BE1-13 | Not Started | Ensure FastAPI auto-docs are complete with descriptions | Medium
BE1-15 | Day 4 | Integration Testing | Test email → creation → approval flow | 2 | BE1-07, BE1-10 | Not Started | Create test cases for complete workflow using pytest | High
BE1-16 | Day 5 | Bug Fixes | Fix issues from Day 4 testing | 3 | BE1-15 | Not Started | Address all critical bugs found in testing | Critical
BE1-17 | Day 5 | Performance Check | Check query performance, add indexes | 1 | BE1-16 | Not Started | Run EXPLAIN on queries, add missing indexes | Medium
BE1-18 | Day 5 | Deployment Prep | Docker setup, environment configs | 2 | BE1-16 | Not Started | Create Dockerfile, docker-compose.yml for easy deployment | High
TOTAL ESTIMATED HOURS:

## Backend Dev 2
BACKEND DEVELOPER 2 - TASK LIST
Focus: Journey Tracking, Asset Management, Supporting Services
ID | Day | Task | Description | Effort (hrs) | Dependencies | Status | Claude Code Prompt | Priority | Notes
BE2-01 | Day 1 | Journey Log Schema | Create journey_logs table | 2 | BE1-01 | Not Started | Create PostgreSQL schema for journey_logs with fields: jlog_id, work_order_id, status, milestones (JSON), expected_timeline (JSON) | Critical | Use provided schema
BE2-02 | Day 1 | Asset Reference Table | Create assets table for lookups | 1.5 | None | Not Started | Create assets table with: asset_id, asset_name, type, location, manufacturer, model | High | Sample data included
BE2-03 | Day 1 | Journey Log Models | SQLAlchemy models for journey logs | 1.5 | BE2-01 | Not Started | Create JourneyLog ORM model with relationships to WorkOrder | Critical
BE2-04 | Day 1 | Asset Lookup Endpoint | GET /assets, GET /assets/{id} | 2 | BE2-02 | Not Started | Create endpoints to search and retrieve asset information | High
BE2-05 | Day 1 | Sample Data Seeding | Create seed data script | 1.5 | BE2-02 | Not Started | Create Python script to populate sample assets, locations for testing | Medium | Helps frontend dev
BE2-06 | Day 2 | Journey Creation Service | Auto-create journey on work order creation | 3 | BE2-03, BE1-05 | Not Started | Create service that automatically creates journey log when work order is created | Critical
BE2-07 | Day 2 | Journey Endpoints | GET /journeys, GET /journeys/{id} | 2 | BE2-06 | Not Started | Create endpoints to retrieve journey logs | High
BE2-08 | Day 2 | Milestone Update | PATCH /journeys/{id}/milestone | 1.5 | BE2-07 | Not Started | Endpoint to update milestone status in journey | Medium
BE2-09 | Day 3 | Work Order History | GET /work-orders/{id}/history | 2 | BE1-05 | Not Started | Endpoint to get status change history for work order | Medium | Audit trail
BE2-10 | Day 3 | Dashboard Stats | GET /dashboard/stats | 2.5 | BE1-05 | Not Started | Endpoint returning counts by status, priority, asset type | High | For frontend dashboard
BE2-11 | Day 3 | Location Endpoints | GET /locations for dropdown | 1.5 | BE2-02 | Not Started | Create endpoints to list locations for forms | Medium
BE2-12 | Day 4 | Bulk Status Update | PATCH /work-orders/bulk/status | 2 | BE1-08 | Not Started | Endpoint to update multiple work orders at once | Low | Nice to have
BE2-13 | Day 4 | Journey Analytics | GET /journeys/analytics | 2 | BE2-07 | Not Started | Return journey completion rates, average times | Low | Phase 2 feature
BE2-14 | Day 4 | Testing Support | Help with integration testing | 3 | BE2-06 | Not Started | Work with BE1 on end-to-end testing | High | Collaborative
BE2-15 | Day 5 | Bug Fixes | Fix issues from testing | 3 | BE2-14 | Not Started | Address bugs in journey and asset services | Critical
BE2-16 | Day 5 | API Performance | Optimize slow queries | 1.5 | BE2-15 | Not Started | Add pagination, optimize joins | Medium
BE2-17 | Day 5 | Documentation | README and API docs | 2 | BE2-15 | Not Started | Write setup instructions and API usage guide | High
TOTAL ESTIMATED HOURS:

## Frontend Dev
FRONTEND DEVELOPER - TASK LIST
Focus: React UI, API Integration, User Experience
ID | Day | Task | Description | Effort (hrs) | Dependencies | Status | Claude Code Prompt | Priority | Notes
FE-01 | Day 1 | React Project Setup | Create React app with routing, state management | 2 | None | Not Started | Create React app with: react-router-dom, axios, react-query, tailwind. Set up folder structure /components, /pages, /api, /hooks | Critical | Use Vite for speed
FE-02 | Day 1 | API Client Setup | Configure axios with base URL and interceptors | 1 | FE-01 | Not Started | Set up axios instance with base URL, error interceptors, auth headers | Critical
FE-03 | Day 1 | Layout Components | Header, sidebar, main layout | 2 | FE-01 | Not Started | Create AppLayout with navigation sidebar and header | High | Use Tailwind
FE-04 | Day 1 | Mock Data | Create mock API responses for development | 1.5 | None | Not Started | Create mock work order data for testing before backend is ready | High | Unblocks development
FE-05 | Day 2 | Work Order List Page | Table view with filters | 4 | FE-02, BE1-05 | Not Started | Create WorkOrderList component with table showing: ID, asset, status, priority, date. Add status and priority filters | Critical | Wait for BE API
FE-06 | Day 2 | List Item Component | Reusable work order card | 1.5 | FE-05 | Not Started | Create WorkOrderCard component for list items | High
FE-07 | Day 2 | Status Badge Component | Visual status indicators | 1 | FE-05 | Not Started | Create StatusBadge with color coding for different statuses | Medium
FE-08 | Day 3 | Work Order Detail Page | Full work order view | 3 | FE-02, BE1-05 | Not Started | Create WorkOrderDetail page showing all fields, with edit capability | Critical
FE-09 | Day 3 | Create Work Order Form | Form for manual creation | 3 | FE-02, BE1-05, BE2-04 | Not Started | Create form with: asset dropdown, location, issue description, priority. Validate on submit | Critical
FE-10 | Day 3 | Approval Action Button | Button to approve work orders | 1.5 | FE-08, BE1-10 | Not Started | Add Approve button on detail page that calls approval endpoint | High
FE-11 | Day 4 | Status Update Modal | Dialog to change work order status | 2 | FE-08, BE1-08 | Not Started | Create modal with status dropdown and notes field | High
FE-12 | Day 4 | Journey Timeline View | Visual journey progress | 2.5 | FE-08, BE2-07 | Not Started | Create timeline component showing journey milestones | Medium | Nice to have
FE-13 | Day 4 | Dashboard Page | Stats and charts overview | 2.5 | BE2-10 | Not Started | Create dashboard with counts by status, priority pie chart | Medium
FE-14 | Day 4 | Loading States | Spinners and skeletons | 1.5 | All pages | Not Started | Add loading indicators to all data fetching | High | Better UX
FE-15 | Day 4 | Error Handling | Error messages and retry | 1.5 | All pages | Not Started | Add error boundaries and user-friendly error messages | High
FE-16 | Day 5 | Polish & Refinement | UI/UX improvements | 3 | All | Not Started | Improve spacing, alignment, colors, responsiveness | High
FE-17 | Day 5 | End-to-End Testing | User flow testing | 2 | All | Not Started | Test complete workflows: create, view, approve, update | Critical
FE-18 | Day 5 | Demo Preparation | Clean up, add sample data | 2 | All | Not Started | Ensure demo environment works smoothly with good data | Critical
TOTAL ESTIMATED HOURS:

## Dependencies
TASK DEPENDENCIES & CRITICAL PATH
Task ID | Task Name | Blocks | Can Start When | Owner | Day
BE1-01 | Database Schema | BE1-03, BE2-01 | Day 1 Start | Backend 1 | Day 1
BE1-03 | Database Models | BE1-05 | BE1-01 Complete | Backend 1 | Day 1
BE1-05 | Basic CRUD | FE-05, FE-08, FE-09 | BE1-03 Complete | Backend 1 | Day 1
BE1-06 | AI Extraction | BE1-07 | BE1-04 Complete | Backend 1 | Day 2
BE1-07 | Email Flow | FE-18 Demo | BE1-06 Complete | Backend 1 | Day 2
BE2-02 | Asset Table | BE2-04, FE-09 | Day 1 Start | Backend 2 | Day 1
BE2-06 | Journey Creation | BE2-07, FE-12 | BE2-03, BE1-05 Complete | Backend 2 | Day 2
FE-01 | React Setup | All FE Tasks | Day 1 Start | Frontend | Day 1
FE-05 | WO List Page | FE-06, FE-07 | FE-02, BE1-05 Complete | Frontend | Day 2
FE-08 | WO Detail Page | FE-10, FE-11 | BE1-05 Complete | Frontend | Day 3
CRITICAL PATH TASKS (Must Complete On Time): |  |  | PARALLEL WORK STREAMS:
1. BE1-01: Database Schema (Day 1) |  |  | Stream 1: Email Processing (BE1)
2. BE1-05: Basic CRUD Endpoints (Day 1-2) |  |  | Stream 2: Journey Tracking (BE2)
3. BE1-07: Email Work Order Flow (Day 2) |  |  | Stream 3: UI Components (FE)
4. FE-01: React Project Setup (Day 1)
5. FE-05: Work Order List Page (Day 2) |  |  | Frontend can start Day 2 with mock data
6. FE-08: Work Order Detail Page (Day 3) |  |  | Backend 2 supports Backend 1 on Day 4-5

## Daily Standup
DAILY STANDUP TRACKER
DAY 1 - Monday April 27
Team Member | Yesterday | Today | Blockers | Help Needed
Backend Dev 1 | N/A | Setup DB schema, API skeleton, email parser POC
Backend Dev 2 | N/A | Create journey schema, asset table, sample data
Frontend Dev | N/A | React setup, layout components, mock data
DAY 2 - Tuesday April 28
Team Member | Yesterday | Today | Blockers | Help Needed
Backend Dev 1
Backend Dev 2
Frontend Dev
DAY 3 - Wednesday April 29
Team Member | Yesterday | Today | Blockers | Help Needed
Backend Dev 1
Backend Dev 2
Frontend Dev
DAY 4 - Thursday April 30
Team Member | Yesterday | Today | Blockers | Help Needed
Backend Dev 1
Backend Dev 2
Frontend Dev
DAY 5 - Friday April 31
Team Member | Yesterday | Today | Blockers | Help Needed
Backend Dev 1
Backend Dev 2
Frontend Dev

## Claude Code Prompts
CLAUDE CODE - PROMPT LIBRARY
Copy these prompts to Claude Code for faster development
Task | Claude Code Prompt | Expected Output | Notes
Database Schema | Create PostgreSQL schema for work_orders table with these fields: - work_order_id (VARCHAR 50, PK) - source (VARCHAR 50) - asset_id, asset_name, location - issue_description (TEXT) - priority (VARCHAR 20) - status (VARCHAR 50) - created_at, updated_at (TIMESTAMP) - criticality, safety, compliance (JSONB) Add appropriate indexes on status, created_at, asset_id | Complete CREATE TABLE statement with indexes | Run in psql or migration tool
FastAPI Setup | Create FastAPI project structure: /api - API endpoints /models - Pydantic models /db - Database connection /services - Business logic Include main.py with FastAPI app initialization, CORS middleware, and /health endpoint. Add requirements.txt with: fastapi, uvicorn, sqlalchemy, psycopg2, pydantic, anthropic, python-dotenv | Complete project folder structure with files | Use uvicorn for dev server
WorkOrder Model | Create SQLAlchemy ORM model for WorkOrder: - Map to work_orders table - Include all fields from schema - Add relationship to JourneyLog - Add __repr__ method - Use PostgreSQL JSONB for criticality, safety, compliance fields | models/work_order.py with complete ORM model | Import in db/base.py
CRUD Endpoints | Create FastAPI CRUD endpoints for work orders: POST /api/work-orders - Create work order GET /api/work-orders - List with filters (status, priority, limit, offset) GET /api/work-orders/{id} - Get single work order PATCH /api/work-orders/{id} - Update work order Use Pydantic models for request/response validation. Return proper HTTP status codes. Include error handling. | api/work_orders.py with all endpoints | Test with curl or Postman
AI Email Extractor | Create service to extract work order info from email using Claude API: Input: email text (subject + body) Output: JSON with {asset, location, issue_description, priority} Use anthropic SDK with this prompt: 'Extract work order information from this email: {email_text} Return JSON with: asset, location, issue_description, priority (low/medium/high/urgent)' Handle API errors gracefully. | services/email_extractor.py with extract_work_order(email_text) function | Set ANTHROPIC_API_KEY in .env
React App Setup | Create React app using Vite: npm create vite@latest work-order-app -- --template react Add dependencies: npm install react-router-dom axios react-query @tanstack/react-query tailwindcss Set up: 1. Tailwind config 2. Router in main.jsx with routes: /, /work-orders, /work-orders/:id 3. API client in api/client.js with axios base URL 4. Folder structure: /components, /pages, /hooks, /api | Complete React project setup | Start with npm run dev
Work Order List Component | Create WorkOrderList component: - Fetch work orders from GET /api/work-orders - Display in table: ID, Asset, Location, Status, Priority, Date - Add filters: status dropdown, priority dropdown, search by asset - Use react-query for data fetching - Show loading spinner while fetching - Status badge with color coding (pending=yellow, approved=green, completed=blue) - Click row to navigate to detail page - Use Tailwind for styling | components/WorkOrderList.jsx | Will need StatusBadge component
Work Order Detail Page | Create WorkOrderDetail page: - Fetch single work order from GET /api/work-orders/{id} - Display all fields in card layout - Show journey timeline if available - Add action buttons: Approve, Update Status, Close - Handle loading and error states - Use Tailwind card styling | pages/WorkOrderDetail.jsx | Add to router
Create Work Order Form | Create form to manually create work order: - Fields: asset (dropdown from /api/assets), location, issue description (textarea), priority (dropdown) - Validate required fields - POST to /api/work-orders on submit - Show success message and redirect to list - Use react-hook-form for validation - Tailwind styling | components/CreateWorkOrderForm.jsx | Add to /create route
Journey Timeline | Create Journey Timeline component: - Props: journeyLog object - Display milestones as vertical timeline - Color code: completed (green), in progress (yellow), pending (gray) - Show dates for completed milestones - Use Tailwind for timeline styling | components/JourneyTimeline.jsx | Shows on detail page

## MVP Scope
MVP SCOPE DEFINITION
IN SCOPE (MVP - Must Have by Friday) | RATIONALE
✓ Email-based work order creation | 5-day sprint requires focus on core functionality
✓ AI extraction of asset, location, issue from email | MVP proves concept and enables user feedback
✓ Work order list view with filters | Complex features (AI assessment, scheduling) need more time
✓ Work order detail view | Phase 2 can build on working foundation
✓ Manual work order creation form
✓ Basic approval workflow (approve button) | DEMO FOCUS
✓ Status update functionality | 1. Show email → work order creation
✓ Journey log creation (auto on WO create) | 2. Display work order list with real data
✓ Basic dashboard with counts | 3. View work order details
✓ Asset and location lookup | 4. Approve a work order
✓ Mock CMMS integration | 5. Update status
6. Show journey log
OUT OF SCOPE (Phase 2 - After Friday)
✗ 15-step intelligent work order engine
✗ AI criticality assessment
✗ Safety condition detection
✗ Compliance tracking
✗ Spare parts availability check
✗ Outlook integration for parts orders
✗ Vendor suggestion system
✗ Smart resource allocation
✗ Smart scheduling
✗ PPM-based work orders
✗ Real CMMS integration
✗ Email notifications
✗ Advanced reporting
✗ Mobile app